## Summary
NVDA P2 Recovery Part 1 — Final Serial Repair
Control | Result | Evidence | Status
Scoped rows | 54 YES / 0 NO | P2_ABSOLUTE_SEMANTIC_READ_LEDGER.tsv | PASS
Execution order | 067–120 strict ascending | serial_repair/SERIAL_EXECUTION_LOG.tsv | PASS
Per-row state records | 54 IN_PROGRESS + 54 COMPLETE | serial_repair/SERIAL_EXECUTION_LOG.tsv | PASS
Per-row mutation proof | 54/54 exact single-row changes | serial_repair/rows/*/NO_OTHER_ROW_CHANGE.txt | PASS
Checkpoints | 6 checksum-preserved checkpoints | checkpoints/SERIAL_REPAIR_* | PASS
Scoped tests | 227 passed; exit 0 | test_outputs/FINAL_SERIAL_ALL_54_TARGETED_TESTS_RAW.txt | PASS
Row validators | 54/54 passed | validation/FINAL_SERIAL_ALL_54_ROW_VALIDATORS_RAW.txt | PASS
Duplicate/generic reasoning | 0 unresolved | validation/FINAL_SERIAL_DUPLICATE_REVIEW.tsv | PASS
Worker-specific paths | 0 | validation/FINAL_SERIAL_VALIDATOR_LOCAL.txt | PASS
Part 1 | COMPLETE for independent audit | Final validator | PASS
P2 | NOT COMPLETE | 78 recovery rows remain outside Part 1 | OPEN
P3 | NOT STARTED | Frozen state | PASS
Next gate | Independent audit of the 54 receipts | Project Manager | OPEN

## Checkpoints
Serial recovery checkpoints
Checkpoint | Completed through | Completed rows | Status
067–076 | 076 | 10 | PASS
077–086 | 086 | 20 | PASS
087–096 | 096 | 30 | PASS
097–106 | 106 | 40 | PASS
107–116 | 116 | 50 | PASS
117–120 | 120 | 54 | PASS